## APPROPRIATIONS BY PROJECT (Modi
PROJ_TITLE | PROJ_ID | PTYPE_NAME | PROJ_DESC | PROJ_ADDR | PPHASE_NAME | FY 2025 | FY 2026 | FY 2027 | FY 2028 | Total Future Years | PROJ_DISTRICT_1 | PROJ_DISTRICT_2 | PROJ_DISTRICT_3 | PROJ_DISTRICT_4 | DEPT_ID_MANAGING | PROJ_LOAD_TO_GIS | DEPT_NAME | DEPT_NAME_MANAGING | PLANNING_PS_BASELINE_START_DT | PLANNING_PS_BASELINE_END_DT | PLANNING_PS_ACTUAL_START_DT | PLANNING_PS_ACTUAL_END_DT | DESIGN_PS_BASELINE_START_DT | DESIGN_PS_BASELINE_END_DT | DESIGN_PS_ACTUAL_START_DT | DESIGN_PS_ACTUAL_END_DT | BIDDING_PS_BASELINE_START_DT | BIDDING_PS_BASELINE_END_DT | BIDDING_PS_ACTUAL_START_DT | BIDDING_PS_ACTUAL_END_DT | CONST_PS_BASELINE_START_DT | CONST_PS_BASELINE_END_DT | CONST_PS_ACTUAL_START_DT | CONST_PS_ACTUAL_END_DT | WARRANTY_PS_BASELINE_START_DT | WARRANTY_PS_BASELINE_END_DT | WARRANTY_PS_ACTUAL_START_DT | WARRANTY_PS_ACTUAL_END_DT | PROJ_CRA
Lauderhill Small Watermains Replacement | FY20150181 | WATERSEWER | The Water Master Plan identifies the replacement as necessary. This will also improve quality of service by improving pressure, fire protection, and water quality. | 300 NW 31st Avenue | Future | 0 | 413431 | 2572170 | 0 | 2985601 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Coral Ridge Country Club Small Watermain | FY20150184 | WATERSEWER | The Water Master Plan identifies the replacement as necessary. This will also improve quality of service by improving pressure and water quality. | 4220 NE 29th Avenue | Future | 0 | 572640 | 4725120 | 0 | 5297760 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Middle River Terrace A-27 Sewer System Rehabilitation | FY20150222 | WATERSEWER | This project will help the City meet its water and sewer infrastructure improvement goals. This sanitary sewer basin was identified as having excessive inflow and infiltration (I&I). | Middle River Terrace | Future | 0 | 7038456 | 0 | 0 | 7038456 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Analysis of Chemical Addition Systems-Peele Dixie | FY20150228 | WATERSEWER | The analysis is expected to yield a new configuration where the bulk tanks are capable of receiving a full load. It will also evaluate if the day tanks are of adequate size to provide at least 24 hours of operations (12 million gallon per day of finished water) before needing to be refilled. Dual tanks will improve reliability and allow for maintenance of one tank without interrupting the plant's operations. | 4030 S State Road 7 | Future | 0 | 109200 | 0 | 0 | 109200 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Wellfield Communications | P12868 | WATERSEWER | This will improve security of the Wellfield with the removal of radio communications and replace with a reliable fiber ring main network. | 3501 West Prospect Road | Future | 208415 | 300000 | 0 | 0 | 508415 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Peele Dixie Membrane Replacement | FY20190737 | WATERSEWER | Anticipated life of membrane elements can be as short as five (5) years. | Peele Dixie Water Treatment Plant | Future | 0 | 0 | 0 | 1500000 | 1500000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Small Water Main Replacement - SW 37th Terrace | FY20190755 | WATERSEWER | The 6-inch and 10-inch water mains in the project scope are more than 60 years old and have failed multiple times. The existing mains are in poor condition and need to be replaced. Failure to replace the mains will result in continued breaks that will cause service interruptions, loss of fire protection, and property damage. Approval of this project will provide improved flow, pressure, and water quality in addition to improved fire protection and lower maintenance costs. | SW 37th Terrace | Future | 0 | 600000 | 3474552 | 0 | 4074552 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
NE 7th Street and NE 2nd Avenue Stormwater Improvements | FY20200820 | FLDSTRM | The existing stormwater infrastructure is not adequate for the area. The location in the densely populated Flagler Village neighborhood is often flooded, which poses a risk to vehicular traffic and pedestrians. | NE 7th Street between 1st Avenue and NE 3rd Avenue | Future | 0 | 0 | 665509 | 0 | 665509 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Flagler Village Neighborhood Improvements | FY20200821 | FLDSTRM | This neighborhood has undersized and aging stormwater infrastructure that is in dire need of upgrading and replacement. This will allow us to assess the condition of the system and develop engineering plans and specification that will rehabilitate the stormwater system within this neighborhood. | Flagler Village HOA | Future | 0 | 672409 | 0 | 0 | 672409 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
SE 8th Street Bridge Replacement | P12863 | BRIDGES | This bridge is 42 years old and the abutment and intermediate bent caps are in poor condition with cracks, spalls, and delamination. Concrete repairs were performed in 2012 and recently cracks have been found in the same location and new locations on the bridge. Concrete repairs near the water only last an average of 5-8 years and this method of repair does not stop the deterioration from occurring at adjacent locations. Also, it is difficult to strengthen the adjacent pre-stressed slab units in a cost-effective manner because of the inability to post-tension adequately. The cost-effective decision is to replace the entire bridge since investing in significant repairs to the substructure units is costly. | SE 8th Street | Future | 3086270 | 0 | 0 | 0 | 3086270 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
George T. Lohmeyer Belt Presses Replacement | P12874 | WATERSEWER | The belt presses were installed in 1999 and have a useful life of approximately 18 years, according to the 2014 Central Regional Wastewater System Renewal and Replacement Requirement Analysis. The belt presses have been maintained for 18 years, and they have reached the end of their useful life. There may be other emerging technologies now available for dewatering biosolids. | 1765 SE 18th Street | Future | 5480777 | 0 | 0 | 0 | 5480777 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Bridge Pipe Assessments | FY20200866 | WATERSEWER | The condition of the existing water and sewer mains located on bridges has not been adequately assessed. It is in the best interest of the City to have these mains inspected and their condition documented in order to properly address the need to repair or replace the mains before they suffer a failure, which could result in environmental non-compliance and regulatory penalties. | City-Wide | Future | 0 | 280000 | 0 | 0 | 280000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Future Parks Projects | FY20210005 | PARKREC | The 2019A portion of the Parks General Obligation Bond will fund the following signature projects in each Commission District including constructing Tunnel Top Park in District 4 atop the northern portion of the Kinney Tunnel above Federal Highway; building a community center at the former site of Lockhart Stadium and developing the surrounding property in District 1; adding a water playground tennis courts sand volleyball courts and a parking garage to Holiday Park in District 2; and building a new community center and other enhancements at Joseph C. Carter Park in District 3. | Citywide | Future | 60000000 | 0 | 0 | 0 | 60000000 | -1 | -1 | -1 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
NW 30th Avenue and NW 17th Court Stormwater Improvements | FY20210943 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | NW 30th Ave & NW 17th CT | Future | 381280 | 0 | 0 | 0 | 381280 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
NE 56th Street and 22nd Avenue Stormwater Improvements | FY20210944 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 2175 NE 56th Street | Future | 708678 | 0 | 0 | 0 | 708678 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
1390 SW 26th Terrace Stormwater Improvements | FY20210945 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1390 SW 26th Terrace | Future | 671009 | 0 | 0 | 0 | 671009 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
1641 SW 28 Terrace Stormwater Improvements | FY20210946 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1641 SW 28 Terrace | Future | 390968 | 0 | 0 | 0 | 390968 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
2555 NE 11th Street Stormwater Improvements | FY20210947 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 2555 NE 11th Street | Future | 415851 | 0 | 0 | 0 | 415851 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
1435 SW 9th Street Stormwater Improvements | FY20210948 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1435 SW 9th Street | Future | 381088 | 0 | 0 | 0 | 381088 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
1200 SE 20th Street Stormwater Improvements | FY20210949 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1200 SE 20th Street | Future | 678281 | 0 | 0 | 0 | 678281 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
1343-1349 Chateau Park Drive Stormwater Improvements | FY20210950 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1343-1349 Chateau Park Drive | Future | 357963 | 0 | 0 | 0 | 357963 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
1161 SW 30 Avenue Stormwater Improvements | FY20210951 | FLDSTRM | This project will address documented stormwater flooding issues, posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1161 SW 30 Ave | Future | 504515 | 0 | 0 | 0 | 504515 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Rio Vista SE 6th Ave Traffic Calming | FY20210979 | ROADST | The ramps on SE 6th Avenue in the project area are for the local surface streets above the Henry Kinney Tunnel. There are significant safety issues along SE 6th Avenue related to vehicle speeds and related to driver confusion as a result of lane drops, both issues negatively impact the safety of pedestrians and cyclists. The safety concerns were identified via a traffic study which showed that 85 percent of vehicles are driving 10 miles above the posted speed limit. Similar speeding concerns were also observed along SE 9th Avenue with radar signs recommended in that study to alleviate the problem. Based on recent inflation costs a 20% increase has been added to the original request. | SE 6th Ave from SE 5th St to Rio Vista Blvd | Future | 287040 | 0 | 0 | 0 | 287040 | 0 | 0 | 0 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
SE 9th Ave Pedestrian Connection | FY20210980 | ROADST | SE 4th Street serves as a parallel road to Las Olas Boulevard and often experiences vehicles traveling at a high rate of speed. The speeding creates dangerous conditions for pedestrians and bicyclists who also use the street, particularly when accessing the water transportation stop or crossing between the Riverside Hotel properties. While there is significant pedestrian crossing at SE 9th Ave, there are no crosswalks at the location; consequently, the addition of crosswalks and a raised intersection aimed at slowing down vehicles will significantly improve safety for all users. Based on current inflation costs a 20% increase to the original request has been added. | SE 9th Ave and SE 4th Street | Future | 199920 | 0 | 0 | 0 | 199920 | 0 | 0 | 0 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Taxiway L & P Extension & Run-Up Area | P12881 | AIRPORTS | Taxiways Lima and Papa are currently in good condition with an area weighted pavement condition index (PCI) value of 75 and 79 respectively. Realigning Taxiways Lima and Papa will result in less complex airfield geometry, which will increase safety, while the new run-up area will reduce departure queue congestion at the end of Runway 9 (north). | 6000 NW 21st Avenue | Future | 495873 | 0 | 0 | 0 | 495873 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Taxiway L & P Extension & Run-Up Area | P12881 | AIRPORTS | Taxiways Lima and Papa are currently in good condition with an area weighted pavement condition index (PCI) value of 75 and 79 respectively. Realigning Taxiways Lima and Papa will result in less complex airfield geometry, which will increase safety, while the new run-up area will reduce departure queue congestion at the end of Runway 9 (north). | 6000 NW 21st Avenue | Future | 367080 | 0 | 0 | 0 | 367080 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Taxiway L & P Extension & Run-Up Area | P12881 | AIRPORTS | Taxiways Lima and Papa are currently in good condition with an area weighted pavement condition index (PCI) value of 75 and 79 respectively. Realigning Taxiways Lima and Papa will result in less complex airfield geometry, which will increase safety, while the new run-up area will reduce departure queue congestion at the end of Runway 9 (north). | 6000 NW 21st Avenue | Future | 6607440 | 0 | 0 | 0 | 6607440 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 9 Western Extension & Parallel Taxiway Extension | P12882 | AIRPORTS | The runway extension will reduce payload penalties for some larger jet aircraft and/or increase aircraft range in addition to increasing capacity. Additionally, the extension will result in a displaced threshold at the western end used only by aircraft departing the airport to the east. The parallel Taxiway Echo will provide necessary access to the proposed runway 9 western extension. | 6000 NW 21st Avenue | Future | 97887 | 925000 | 0 | 0 | 1022887 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 9 Western Extension & Parallel Taxiway Extension | P12882 | AIRPORTS | The runway extension will reduce payload penalties for some larger jet aircraft and/or increase aircraft range in addition to increasing capacity. Additionally, the extension will result in a displaced threshold at the western end used only by aircraft departing the airport to the east. The parallel Taxiway Echo will provide necessary access to the proposed runway 9 western extension. | 6000 NW 21st Avenue | Future | 40300 | 725000 | 0 | 0 | 765300 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 9 Western Extension & Parallel Taxiway Extension | P12882 | AIRPORTS | The runway extension will reduce payload penalties for some larger jet aircraft and/or increase aircraft range in addition to increasing capacity. Additionally, the extension will result in a displaced threshold at the western end used only by aircraft departing the airport to the east. The parallel Taxiway Echo will provide necessary access to the proposed runway 9 western extension. | 6000 NW 21st Avenue | Future | 725400 | 13050000 | 0 | 0 | 13775400 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
1410-1415 SW 24th Court Stormwater Improvements | FY20221010 | FLDSTRM | The project will address historical stormwater flooding issues at the site by replacing and installing a new stormwater infrastructure. | 1401-1415 SW 24 Ct | Future | 0 | 437035 | 0 | 0 | 437035 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
2175 NE 56th Street Stormwater Improvements | FY20221012 | FLDSTRM | The project will address historical stormwater flooding issues at the site by replacing and installing a new stormwater infrastructure. | 2175 NE 56 St | Future | 0 | 568551 | 0 | 0 | 568551 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
811 NW 57th Place Stormwater Improvements | FY20221013 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risks to vehicular traffic and pedestrians by installing new stormwater infrastructure. | 811 NW 57th Place | Future | 0 | 730574 | 0 | 0 | 730574 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
West Las Olas Stormwater Improvements | FY20221014 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risks to vehicular traffic and pedestrians by installing new stormwater infrastructure and improving the existing infrastructure. | 700 Block of West Las Olas Blvd | Future | 0 | 846669 | 0 | 0 | 846669 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
940 SW 8th Street Stormwater Improvements | FY20221015 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 940 SW 8th Street | Future | 0 | 481141 | 0 | 0 | 481141 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Imperial Point Neighborhood Stormwater Improvement | FY20221016 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 2201 Imperial Point Dr | Future | 0 | 398082 | 0 | 0 | 398082 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
2420 Aqua Vista Blvd Stormwater Improvements | FY20221017 | FLDSTRM | This project will address documented stormwater flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 2420 Aqua Vista Blvd | Future | 0 | 504648 | 0 | 0 | 504648 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Poinsettia Heights North Shore Neighborhood Stormwater Infra | FY20221018 | FLDSTRM | This project will address documented stormwater and tidal flooding issues posing safety risk to vehicle traffic and pedestrians by installing new stormwater infrastructure. | 1701 Poinsettia Dr | Future | 0 | 566668 | 0 | 0 | 566668 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
George T. Lohmeyer Wastewater Treatment Plant Sludge Pump Re | FY20221035 | WATERSEWER | The CDM Smith 20-Year Renewal and Replacement report states that the sludge pump is close to the end of its useful life and needs to be replaced. | 1765 SE 18th Street | Future | 0 | 3705156 | 0 | 0 | 3705156 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
George T. Lohmeyer Wastewater Treatment Plant Secondary Serv | P12875 | WATERSEWER | Currently, both the primary and the secondary servers at GTL are located in the same location and separating them would provide the plant with greater resiliency. | 1765 SE 18th Street | Future | 100000 | 100000 | 0 | 0 | 200000 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
George T. Lohmeyer Wastewater Treatment Plant Clarifier Reha | P12876 | WATERSEWER | The CDM Smith 20-Year Renewal and Replacement report states that the existing concrete is over forty years old and no longer level. | 1765 SE 18th Street | Future | 7878333 | 0 | 0 | 0 | 7878333 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Duplex Pumping Stations Rehabiliation /Replacement | FY20221046 | WATERSEWER | The identified waste water pumping stations have exceeded their life expectancy, and the pumps, motors, and essential equipment are no longer supported by the manufacturer. Stations should be resized based on current and future expected waste water flows. Some of the structures are also no longer viable and will require replacement and/or relocation. | Various location - 5 pump stations | Future | 0 | 582360 | 0 | 5402310 | 5984670 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Hardening of Wastewater Generators | FY20221048 | WATERSEWER | The Reiss 2017 Wastewater Comprehensive Utility Strategic Master Plan risk assessment recommends the installation of emergency stand-by diesel generators to maintain waste water services to critical infrastructure. A comprehensive risk analysis was performed and can be found in section WW-6 of the Reiss Master Plan. | Various locations -12 pump stations | Future | 0 | 0 | 3015000 | 0 | 3015000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Bayview Drive North Bike Lanes | FY20221050 | ROADST | Bayview Drive currently has 4.6 miles of bike lane from Sunrise Boulevard to NE 60th Ave providing a north/south route for bicyclists that connects to the bike lanes on Sunrise Blvd to the Beach but is missing the approximately 1000 feet to connect to US1/Federal Highway and NE 62nd Street. This connection will fill an important gap in the network that is highly used by bicyclists as seen through Strava data and previous bike counts collected by the City. There is existing pavement width to complete this project. Florida Department of Transportation (FDOT) will be completing a resurfacing project on US1 at this area which will improve bike facilities making this an even more important missing link. Based on recent inflation a 20% increase has been added to the original request. | Bayview Drive - NE 60th St to US1/Federal Highway | Future | 18000 | 0 | 120000 | 0 | 138000 | -1 | 0 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Sewer Basin D-19 Collection System Rehabilitation (I&I) | NEW - FY 2023033 | WATERSEWER | Sewer Pump Station D-19 is experiencing extremely high pump run times. This is mainly due to I&I (Inflow and infiltration), which allows excessive groundwater and sand into the sewer system, wearing out the pumps at Pump Station D-19 and causing extreme flow and capacity issues at George T. Lohmeyer Wastewater Treatment Plant (GTL). I&I (Inflow and infiltration) must be reduced throughout the City to improve capacity at George T. Lohmeyer Wastewater Treatment Plant (GTL) and to extend the life of our pipes and pumps. | 509 Royal Plaza Drive | Future | 912926 | 0 | 0 | 0 | 912926 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
1108 SW 25th Avenue Stormwater Improvements | NEW - FY 2023049 | FLDSTRM | This project is needed to address documented flooding issues that pose safety risks to vehicle traffic and pedestrians by installing new storm water infrastructure. | 1108 SW 25th Ave | Future | 0 | 0 | 1001910 | 0 | 1001910 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
PBS-2739 NE 14th Street Stormwater Improvements | NEW - FY 2023051 | FLDSTRM | This project is needed to address documented flooding issues that pose safety risks to vehicle traffic and pedestrians by installing new storm water infrastructure. | 2739 NE 14th Street | Future | 0 | 0 | 384774 | 0 | 384774 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
PBS-3030 Holiday Drive Stormwater Improvements | NEW - FY 2023052 | FLDSTRM | The replacement of the storm water outfall pipe will solve flooding issues at Holiday Drive & adjacent properties that pose safety risks to vehicle traffic and pedestrians. | 3030 Holiday Drive | Future | 0 | 0 | 537978 | 0 | 537978 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
PBS-611- 829 Ponce de Leon Drive Stormwater Improvements | NEW - FY 2023053 | FLDSTRM | This project is needed to address documented flooding issues that pose safety risks to vehicle traffic and pedestrians by installing new storm water infrastructure. | 611-829 Ponce De Leon Drive | Future | 0 | 0 | 843763 | 0 | 843763 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
6711 NE 21st Avenue Stormwater Improvements | NEW - FY 2023054 | FLDSTRM | This project is needed to address documented flooding issues that pose safety risks to vehicle traffic and pedestrians by installing new storm water infrastructure. | 6711 NE 21st Ave | Future | 0 | 0 | 1286790 | 0 | 1286790 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Sewer Basin D-20 Collection System Rehabilitation (I&I) | NEW - FY2023034 | WATERSEWER | Sewer Pump Station D-20 is experiencing extremely high pump run times. This is mainly due to Inflow and infiltration (I&I), which allows excessive groundwater and sand into the sewer system, wearing out the pumps at Pump Station D-20 and causing extreme flow and capacity issues at George T. Lohmeyer Wastewater Treatment Plant (GTL). Inflow and infiltration (I&I) must be reduced throughout the City to improve capacity at George T. Lohmeyer Wastewater Treatment Plant (GTL) and to extend the life of our pipes and pumps. | 433 Isle of Palms | Future | 910480 | 0 | 0 | 0 | 910480 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
NW 13th Street 24" Force Main Replacement - Phase 2 & 3 | NEW-000353 | WATERSEWER | This section of the force main is one of the oldest in the City's system and has exceeded its life cycle, making it susceptible to breakage and possible sanitary sewer overflows (SSO). The force main condition assessment, under the consent order, has identified these sections for replacement. | NW 13th Street from SR 845 to SR 811 | Future | 0 | 3939778 | 0 | 0 | 3939778 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
West Lake Drive Bridge over Mercedes River Replacement | P12858 | BRIDGES | The superstructure of the bridge is rated as category “3 -Serious”. The sufficiency rating is 7.3 with a Health Index of 27.2. It is designated as “Structurally Deficient” by the Florida Department of Transportation (FDOT) based on the National Bridge Inspection Standards (NBI). Instead of the typical 24-month cycle the FDOT inspection frequency was set to 6-months cycle due to ongoing deficiencies of the beams and bent caps affecting the loadbearing capacity of the structure. The weight limit for the bridge is at 16 tons or below for two-axle vehicle. | West Lake Drive over Mercedes River | Future | 0 | 0 | 1509478 | 0 | 1509478 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Shady Banks Stomwater Improvements | NEW-058895 | FLDSTRM | The Shady Banks neighborhood has been susceptible to moderate to intense flooding during the past years. The majority of the flooding is concentrated within the center of the neighborhood, at the intersection of SW 14th Street, SW 18th Avenue and SW 13th Court. This intersection is one of the lowest areas in the Shady Banks neighborhood and is not hydraulically connected to a body of water. | SW 14th Street | Future | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Prospect Wellfield West Generator Replacement | NEW-094105 | WATERSEWER | The existing generator is past its useful life, The generator was rebuilt in 2008 and does not meet current emission standards. | 3501 W. Prospect Road | Future | 0 | 0 | 0 | 4336794 | 4336794 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Design and Construct FXE Maintenance Apron Pavement Rehab Project | P12883 | AIRPORTS | The 2023 Airport Pavement Evaluation Report for Florida Department of Transportation (FDOT) indicates that pavement condition index (PCI) for the airport maintenance building apron area is 62. The apron area is mostly a staging and parking area for heavy airport equipment and vehicles. The area also has high frequency usage of vehicles. The PCI may become significantly lower in a short timeframe if maintenance of the pavement is not done properly or timely. The rehabilitation of the pavement could extend the asphalt life up to an additional 15 years. | 6000 NW 21st Avenue | Future | 187646 | 0 | 0 | 0 | 187646 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Design and Construct FXE Maintenance Apron Pavement Rehab Project | P12883 | AIRPORTS | The 2023 Airport Pavement Evaluation Report for Florida Department of Transportation (FDOT) indicates that pavement condition index (PCI) for the airport maintenance building apron area is 62. The apron area is mostly a staging and parking area for heavy airport equipment and vehicles. The area also has high frequency usage of vehicles. The PCI may become significantly lower in a short timeframe if maintenance of the pavement is not done properly or timely. The rehabilitation of the pavement could extend the asphalt life up to an additional 15 years. | 6000 NW 21st Avenue | Future | 493000 | 0 | 0 | 0 | 493000 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
SE 7th Street Bridge over Rio Cordova Replacement | P12859 | BRIDGES | The SE 7th Street bridge is in poor condition based on the National Bridge Inspection Standards (NBI) and Florida Department of Transportation (FDOT) guidelines. The bridge is rated as a category 4 (poor) in 2 of the 4 main elements of the structure and has a sufficiency rating of 25.9, designating the bridge structurally deficient by FDOT and NBI standards. The NBI rating for the deck and superstructure remains at a 4 due to the transverse cracks and exposed strands in several slab units. The close proximity of the structure’s underside to the channel with brackish water creates a limitation for a successful repair of this condition and a complete bridge replacement is necessary. | SE 7th Street over Rio Cordova SE 7th Street over Rio Cordova | Future | 0 | 0 | 1050797 | 0 | 1050797 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Watershed Asset Management Plan (WAMP) - Condition Assessment | P12888 | FLDSTRM | This initiative will allow City staff to properly assess the current state of storm water assets, the level of service required, as well as the best operational and maintenance investment strategies. The results from this initiative will fundamentally shape operational schedules and guide future capital improvement plans. This project will ensure the desired level of service for drainage across the City and reduce the frequency, intensity, and duration of flooding in the face of extreme rainfall and sea level rise. | Citywide | Future | 3750000 | 3750000 | 3750000 | 3750000 | 15000000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Sodium Hypochlorite Conversion at George T. Lohmeyer Wastewater Treatment Plant | NEW-246681 | WATERSEWER | Chlorine Is currently used at the facility to control biological growth on process equipment and piping. Gaseous chlorine costs have doubled and are projected to continue to increase. Switching to a bulk hypochlorite solution will lower operational costs and increase safety at the plant. | 1801 Eisenhower Boulevard | Future | 0 | 0 | 0 | 14145246 | 14145246 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
SE 12th Street Stormwater Improvements | NEW-317019 | FLDSTRM | Due to the condition of the storm water infrastructure, replacement is required to ensure flooding does not occur during heavy rain fails. | SE 12 St and Cordova Rd | Future | 0 | 0 | 0 | 565293 | 565293 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Oakland Park Parking Lot Improvements | NEW-338020 | PARKING | Update the Oakland Park Boulevard parking lots to maximize parking availability and maintain existing facilities. | Oakland Park Boulevard Area | Future | 2500000 | 0 | 0 | 0 | 2500000 | -1 | 0 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
West Lake Drive Bridge over Estelle River Replacement | P12860 | BRIDGES | The sufficiency rating is 15.4 with a health Index of 38.45 for this project. It is designated as “Functionally Obsolete” by the Florida Department of Transportation (FDOT) based on the National Bridge Inspection Standards (NBI). Instead of the typical 24-month cycle, the FDOT inspection frequency was set to 3-months cycle due to ongoing deficiencies of the beams and bent caps affecting the loadbearing capacity of the structure. The weight limit for the bridge is at 10 tons or below for two-axle vehicles. | West Lake Drive Bridge at Estelle River | Future | 0 | 0 | 1096666 | 0 | 1096666 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Carter Park Pool | NEW-381194 | SPECREC | The pool provides vital learn to swim lessons to over 500 children and adults each year, as well as partnering with Swim Central to offer additional lessons to local elementary schools. In addition to teaching swim lessons to the community, the pool also offers continuous lap swim for swimmers looking to exercise and improve their stroke, and open recreational swim. The pool also has a water playground that is accessible during recreational swim hours for ages 7 and under. | 1450 W Sunrise Blvd | Future | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | -1 | 0 | PRD | Yes | Parks and Recreation | Parks and Recreation
SW 5th Avenue and SW 2nd Street Stormwater Improvements | NEW-429333 | FLDSTRM | This project is needed to address existing pipes that have joint damage causing roadway deterioration that is occurring along SW 5th Avenue between Broward Blvd and Esplanade Park. | SW 5 Ave and SW 2 St | Future | 0 | 0 | 0 | 1526526 | 1526526 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Pump Station D-1 Gravity Sewer Rehabilitation | NEW-460962 | WATERSEWER | This project is expected to reduce the infiltration and inflow (I&I) at Pump Station-D-1, reducing wastewater treatment needs at the George T. Lohmeyer Regional Wastewater Treatment Plant (GTLWWTP). | City-wide | Future | 420478 | 0 | 0 | 0 | 420478 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
900 NE 20th Avenue Stormwater Improvements | NEW-471001 | FLDSTRM | This project is needed to address documented flooding issues by replacing obsolete and damaged storm water infrastructure. | 900 NE 20th Ave | Future | 0 | 0 | 0 | 323935 | 323935 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Design/Build flow meters Pump Stations A23, D36, A17, D39, D28, E5, B10, B23, D29, D26, & D27 | NEW-481949 | WATERSEWER | This project is required in order to document the reduction of infiltration and inflow (I&I) at Pump Stations A23, D36, A17, D39, D28, E5, B10, B23, D29, D26, and D27. The City has been put on notice by the Florida Department of Environmental Protection (FDEP). If the City does not reduce I&I at the George T. Loyhmeyer Wastewater Treatment Plant, then the City may be directed to slow down future development efforts within the City. | City-Wide | Future | 0 | 0 | 2112000 | 0 | 2112000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
TAM-Las Olas Garage Improvements | NEW-487346 | PARKING | This project ensures future proper maintenance of the garage. | 200 Las Olas Circle | Future | 250000 | 0 | 0 | 0 | 250000 | 0 | -1 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
SE 17 Street and Cordova Road Stormwater Improvements | NEW-500621 | FLDSTRM | This project is needed to repair damaged pipes that are causing roadway deterioration along Cordova Road between SE 18th Street and SE 16th Street. | SE 17 St and Cordova Rd | Future | 0 | 0 | 0 | 1496592 | 1496592 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
SE Croissant Park Water Main Upgrades | NEW-506357 | WATERSEWER | The 6-inch and 8-inch water mains in the project scope have failed multiple times due to age and corrosion. The existing mains are in poor condition and need to be replaced. Failure to replace the mains will result in continued breaks that will cause service interruptions, loss of fire protection, and property damage. | SW 4 Avenue & SW 22 Street | Future | 0 | 0 | 0 | 4531868 | 4531868 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Beachwalk Improvements at Park Tower Tunnel | NEW-528306 | OTHPHEV | This request will mitigate future risks and liabilities associated with the abandoned tunnel. | 1151 N Fort Lauderdale Beach | Future | 0 | 0 | 0 | 100000 | 100000 | 0 | -1 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
NW 9th Court Stormwater Improvements | NEW-537952 | FLDSTRM | This project is needed to implement storm water improvements that will help reduce documented flooding issues. Flooding poses safety risks to vehicle traffic and pedestrians, and the improvements will also enhance the neighborhood overall. | 2208 NW 9th Court | Future | 0 | 0 | 345093 | 0 | 345093 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Riverland Road Safety and Traffic Calming | NEW-605883 | ROADST | Riverland Road has experienced a significant increase in vehicle cut-through traffic since the advent of GPS navigation apps. Based on a recent study, approximately 30% of the vehicles on this two-lane residential street are traveling from SR 7 to Davie Blvd. Based on past traffic studies, there are also speeding issues occurring which pose safety concerns for pedestrians and bicyclists along this frequently used route. Additionally, since there is a school located on the corridor, children walking or biking to school must frequently contend with safety issues as well. The City committed to this project after the TIGER grant was completed. | Riverland Road from SR7 to Davie Road | Future | 0 | 0 | 1000000 | 0 | 1000000 | 0 | 0 | -1 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Design and Construction of Taxiway Echo Pavement Rehabilitation | P12884 | AIRPORTS | Taxiway Echo is currently in poor condition with an area weighted pavement condition index (PCI) value of 52. However, the 2023 Florida Department of Transportation (FDOT) pavement evaluation report recommended this taxiway be milled and overlaid in the short term due to some areas of Taxiway Echo that are significantly under distress. | 6000 NW 21st Avenue | Future | 596686 | 0 | 0 | 0 | 596686 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Design and Construction of Taxiway Echo Pavement Rehabilitation | P12884 | AIRPORTS | Taxiway Echo is currently in poor condition with an area weighted pavement condition index (PCI) value of 52. However, the 2023 Florida Department of Transportation (FDOT) pavement evaluation report recommended this taxiway be milled and overlaid in the short term due to some areas of Taxiway Echo that are significantly under distress. | 6000 NW 21st Avenue | Future | 2048000 | 0 | 0 | 0 | 2048000 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
234 Plaza Las Olas Stormwater Improvements | NEW-650504 | FLDSTRM | This project will address documented flooding issues that pose safety risks to vehicle and pedestrian traffic. These risks can be mitigated by installing new storm water infrastructure. | 234 Plaza Las Olas | Future | 0 | 0 | 0 | 298979 | 298979 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Bayshore Drive Forcemain Phase II | NEW-666519 | WATERSEWER | The force main extension is required to provide redundancy in case the main 48-inch force main is unavailable. | NE 8th Street and 15th Avenue | Future | 0 | 0 | 0 | 3807206 | 3807206 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
P3 Heron Bay Garage | NEW-699105 | FIRE | The fire station will serve the Las Olas Corridor and surrounding communities. This is a rapidly growing and heavily populated area of the City and a new station will help increase the quality of service. | Las Olas - E 10th Avenue | Future | 0 | 6150000 | 0 | 0 | 6150000 | 0 | -1 | 0 | -1 | FIR | Yes | Fire Rescue | Fire Rescue
Annual Sidewalk Gap Construction | P12865 | ROADST | Additional sidewalks will improve the safety for walking pedestrians, make neighborhoods more walkable, and reduce the number of vehicles on the road. | Citywide | Future | 950000 | 900000 | 1100000 | 2500000 | 5450000 | -1 | -1 | -1 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Design/Build flow meters & I/C for Pump Stations D21, D20, D1, A27, D49, A12, A29, B12, D53 & D30 | NEW-721738 | WATERSEWER | This project is required in order to document the reduction of infiltration and inflow (I&I) at Pump Stations D21, D20, D1, A27, D49, A12, A29, B12, D53, & D30. The City has been put on notice by the Florida Department of Environmental Protection (FDEP). If the City does not reduce I&I at the George T. Loyhmeyer Wastewater Treatment Plant, then the City may be directed to slow down future development efforts within the City. | City-wide | Future | 1957500 | 0 | 0 | 0 | 1957500 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Excavate and Dispose of Dry Lime Sludge | P12869 | WATERSEWER | Dry lime sludge must be removed from the sludge storage areas periodically as the sludge is continually produced as a by-product of the Fiveash Water Treatment Plant. Removing dry lime ludge increases capacity, improves treatment, and reduces the need for costly and disruptive mechanical dredging. | 3317 NW 56th Street (Prospect Road) 3317 NW 56th Street | Future | 6000000 | 0 | 0 | 0 | 6000000 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
SW 12th Court Stormwater Improvements | NEW-736864 | FLDSTRM | This project will address documented storm water flooding that pose a safety risk to vehicle traffic and pedestrians by installing new storm water infrastructure. | 3525 SW 12TH Court | Future | 0 | 0 | 0 | 443045 | 443045 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
West Lake Drive Bridge over Lucille River Replacement | P12861 | BRIDGES | The superstructure of the bridge is rated as category “3 -Serious”. The sufficiency rating is 7.3 with a Health Index of 26.72. It is designated as “Structurally Deficient” by the Florida Department of Transportation (FDOT) based on the National Bridge Inspection Standards (NBI). Instead of the typical 24-month cycle, the FDOT inspection frequency was set to 6-months cycle due to ongoing deficiencies of the beams and bent caps affecting the loadbearing capacity of the structure. The weight limit for the bridge is at 16 tons or below for two-axle vehicle. | West Lake Drive over Lucille River | Future | 0 | 0 | 1249558 | 0 | 1249558 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
TAM-City Hall Parking Garage Improvements | P12879 | PARKING | This project ensures future proper maintenance of the garage. | 100 N Andrews Avenue | Future | 0 | 1000000 | 0 | 0 | 1000000 | 0 | -1 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
South Melrose Manors Small Water Main Replacement | NEW-868698 | WATERSEWER | Over the many years of use, the existing cast iron watermains have buildup inside which restricts flow. A replacement of the water mains will allow water to flow more easily and increase the water pressure for residents in the area. | 2965 SW 11th Court | Future | 0 | 0 | 0 | 8667700 | 8667700 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Water Main Crossing of the Intracoastal at Oakland Park Boulevard | NEW-877588 | WATERSEWER | The existing, 16-inch water main was installed in 1957 and is well past its anticipated service life. The City's Comprehensive Utility Strategic Master Plan included a recommendation to replace the existing water main with a 24-inch water main crossing to accommodate future growth on the barrier island. | 3200 E. Oakland Park Blvd. | Future | 0 | 0 | 0 | 1510996 | 1510996 | -1 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Pump Station D-3 Gravity Sewer Rehabilitation | NEW-887882 | WATERSEWER | This project will reduce the infiltration and inflow (I&I) of storm water at Pump Station-D-3. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 2601 Sea Island Drive | Future | 918660 | 0 | 0 | 0 | 918660 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Parking Facility Electric Vehicle Charging Stations | P12880 | PARKING | To support the the City's internal fleet and private drivers, the Transportation and Mobility Department is requesting additional EV charging stations. The estimated cost to add one (1) charging station is approximately $7,500. This cost includes the electric installation, the charging station post, and the vehicle charging station itself. In order to add twenty (20) charging stations per year, staff is requesting $150,000 per year to implement this public service. To support the implement of this project, Fort Lauderdale City Ordinance allows the Parking Fund to charge additional fees to any parking space with an electric vehicle charging station. | Citywide | Future | 150000 | 150000 | 150000 | 150000 | 600000 | -1 | -1 | -1 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Pump Station B-12 Gravity Sewer Rehabilitation | NEW-910927 | WATERSEWER | This project is expected to reduce the infiltration and inflow (I&I) at Pump Station-B-12 .I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 5900 Bayview Drive | Future | 0 | 0 | 1524253 | 0 | 1524253 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Citywide Seawall Assessment Masterplan | NEW-920344 | ROADST | Many city-owned seawalls are in need of replacement due to overtopping and structurally deficiency. Systematic replacement of these seawalls will greatly improve the flooding conditions and the overall surrounding community, as well as stabilize adjacent roadways and green spaces, critical to the functionality of the city. | City-wide | Future | 0 | 542304 | 0 | 0 | 542304 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Design/Build flow meters for Pump Stations D24, B1, B4, D4, E3, D23, B9, D25, B13 and A33 | NEW-928643 | WATERSEWER | This project is required in order to document the reduction of infiltration and inflow (I&I) at Pump Stations D24, B1, B4, D4, E3, D23, B9, D25, B13, and A33. The City has been notified by the Florida Department of Environmental Protection (FDEP) and informed that if I&I is not reduced at the George T. Loyhmeyer (GTL) Wastewater treatment plant, then the City may be directed to slow down development within the City. | City-wide | Future | 0 | 1957500 | 0 | 0 | 1957500 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
NE 26th Street Complete Streets | NEW-932113 | ROADST | This project supports the FY 2024 Commission Priority of reducing traffic congestion and enhancing the ability of people to move around the City as development downtown increases. This project has been submitted for transportation surtax and Complete Streets & Localized Initiatives Program (CSLIP) funding but has not been awarded to date. | NE 26 Street between US1 and Bayview Drive | Future | 0 | 0 | 525000 | 0 | 525000 | -1 | 0 | 0 | 0 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Undergrounding Program | NEW-954605 | HUD | Neighborhoods are submitting applications to underground the overhead utility wires in their community. This program provides the funding to start the undergrounding of neighborhoods and supports staff in establishing a special assessment process to generate additional revenue to pay for additional, associated costs. The actions are through a reimbursement process, requiring certain funds to be available for the project’s preliminary designs. | Citywide | Future | 0 | 0 | 0 | 681000 | 681000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Runway 13-31 Pavement Rehabilitation Project | NEW-955211 | AIRPORTS | Runway 13-31 is currently in fair condition with an area weighted PCI value of 59. The pavement and intersection were seal coated in 2023 to temporarily improve the condition of the runway. However, the 2023 Florida Department of Transportation (FDOT) pavement inspection report recommended Runway 13-31 be milled and overlayed with P-401 asphalt for a long term improvement, which typically takes place five years after the sealcoating. | 6000 NW 21st Avenue | Future | 0 | 33750 | 122500 | 368265 | 524515 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 13-31 Pavement Rehabilitation Project | NEW-955211 | AIRPORTS | Runway 13-31 is currently in fair condition with an area weighted PCI value of 59. The pavement and intersection were seal coated in 2023 to temporarily improve the condition of the runway. However, the 2023 Florida Department of Transportation (FDOT) pavement inspection report recommended Runway 13-31 be milled and overlayed with P-401 asphalt for a long term improvement, which typically takes place five years after the sealcoating. | 6000 NW 21st Avenue | Future | 0 | 0 | 22500 | 340000 | 362500 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 13-31 Pavement Rehabilitation Project | NEW-955211 | AIRPORTS | Runway 13-31 is currently in fair condition with an area weighted PCI value of 59. The pavement and intersection were seal coated in 2023 to temporarily improve the condition of the runway. However, the 2023 Florida Department of Transportation (FDOT) pavement inspection report recommended Runway 13-31 be milled and overlayed with P-401 asphalt for a long term improvement, which typically takes place five years after the sealcoating. | 6000 NW 21st Avenue | Future | 0 | 0 | 405000 | 6120000 | 6525000 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Lightning Predictor | NEW-955973 | PARKREC | Installation of these outdoor warning systems will ensure that all park users remain safe when dangerous weather is in the area of the above mentioned parks. The warning systems will also minimize the disruption that dangerous weather presents to recreation activities by alerting staff when lightning no longer poses a threat to the area. | Citywide | Future | 0 | 173000 | 0 | 0 | 173000 | -1 | -1 | -1 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
Pump Station A-12 Gravity Sewer Rehabilitation | NEW-FY 2023023 | WATERSEWER | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station-A-12. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 900 Avocado Isle | Future | 0 | 8155197 | 0 | 0 | 8155197 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station A-14 Gravity Sewer Rehabilitation | NEW-FY 2023024 | WATERSEWER | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station-A-12. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 1750 N Federal Highway | Future | 7061700 | 0 | 0 | 0 | 7061700 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-21 Gravity Sewer Rehabilitation | NEW-FY 2023035 | WATERSEWER | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station D-21. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 646 Famingo Drive | Future | 718276 | 0 | 0 | 0 | 718276 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-24 Gravity Sewer Rehabilitation | NEW-FY 2023037 | WATERSEWER | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station D-24. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 2209 Sunrise Key Boulevard | Future | 0 | 0 | 1328626 | 0 | 1328626 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-30 Gravity Sewer Rehabilitation | NEW-FY 2023038 | WATERSEWER | This project is required in order to reduce I&I at PS D-30 and ultimately at GTLWWTP. The City has been put on notice by FDEP that if we do not reduce I&I flows and show proof of such reduction at the GTLWWTP plant or at the localized PSs level, where we have completed sewer rehabilitations, we may be directed to slow down redevelopment within the City until we provide proof of I&I flow reduction. | 1245 West Lake Drive | Future | 0 | 0 | 809023 | 0 | 809023 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-41 Gravity Sewer Rehabilitation | NEW-FY 2023040 | WATERSEWER | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station D-41. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 431 N. Birch Road | Future | 2052472 | 0 | 0 | 0 | 2052472 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-46 Gravity Sewer Rehabilitation | NEW-FY 2023041 | WATERTRANS | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station D-46. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 1700 S.E. 7th Street | Future | 1412862 | 0 | 0 | 0 | 1412862 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-49 Gravity Sewer Rehabilitation | NEW-FY 2023042 | WATERTRANS | Sewer Pump Station D-49 is experiencing extremely high pump run times. This is mainly due to I&I (Inflow and infiltration), which allows excessive groundwater and sand into the sewer system, wearing out the pumps at Pump Station D-49 and causing extreme flow and capacity issues at George T. Lohmeyer Wastewater Treatment Plant (GTL). I&I (Inflow and infiltration) must be reduced throughout the City to improve capacity at George T. Lohmeyer Wastewater Treatment Plant (GTL) and to extend the life of our pipes and pumps. | 1717 S.E. 10 Street | Future | 0 | 616106 | 0 | 0 | 616106 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Pump Station D-53 Gravity Sewer Rehabilitation | NEW-FY 2023043 | WATERTRANS | This project will reduce the Infiltration and Inflow (I&I) of storm water in the sewer network for Pump Station D-53. I&I of storm water requires additional treatment needs at the George T. Lohmeyer Wastewater Treatment Plant (GTLWWTP). Completing this project will reduce the City's reliance on treatment and provide relief to the root cause of I&I. | 1615 S.E. 14th Street | Future | 0 | 0 | 1294420 | 0 | 1294420 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Sewer Basin D-8 Collection System Rehabilitation (I&I) | NEW-FY 2023045 | WATERTRANS | Sewer Pump Station D-8 is experiencing extremely high pump run times. This is mainly due to I&I (Inflow and infiltration), which allows excessive groundwater and sand into the sewer system, wearing out the pumps at Pump Station D-8 and causing extreme flow and capacity issues at George T. Lohmeyer Wastewater Treatment Plant (GTL). I&I (Inflow and infiltration) must be reduced throughout the City to improve capacity at George T. Lohmeyer Wastewater Treatment Plant (GTL) and to extend the life of our pipes and pumps. | 105 Nurmi Drive | Future | 1280986 | 0 | 0 | 0 | 1280986 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Sewer Basin D-9 Collection System Rehabilitation | NEW-FY 2023046 | WATERTRANS | Sewer Pump Station D-9 is experiencing extremely high pump run times. This is mainly due to Inflow and infiltration (I&I), which allows excessive groundwater and sand into the sewer system, wearing out the pumps at Pump Station D-9 and causing extreme flow and capacity issues at George T. Lohmeyer Wastewater Treatment Plant (GTL). Inflow and infiltration (I&I) must be reduced throughout the City to improve capacity at George T. Lohmeyer Wastewater Treatment Plant (GTL) and to extend the life of our pipes and pumps. | 95 Fiesta Way | Future | 508549 | 0 | 0 | 0 | 508549 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
West Lake Drive Over Diane River Bridge Replacement | NEW-FY 2023059 | BRIDGES | The Laguna bridge is in poor condition based on the National Bridge Inspection Standards and Florida Department of Transportation (FDOT) guidelines. The bridge has a sufficiency rating of 41.6 and a health index of 35.36. FDOT considers the bridge functionally obsolete. Originally the bridge was constructed in 1958. As per the last FDOT inspection report, the bridge has several deficiencies: exposed rebars and concrete spalling. These deficiencies are caused by the proximity of the bridge to brackish or salted water. If not addressed, the chloride contamination will continue and further deteriorate the structure. | Laguna Terrace over Diane River | Future | 0 | 0 | 1906704 | 2620596 | 4527300 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Irrigation Upgrades - Lauderdale Memorial Park Cemetery | NEW-FY 20240002 | OTHPHEV | The existing irrigation system at Lauderdale Memorial Park Cemetery has become inefficient due to its age and use. Repairs to the failing main lines are more frequent. This is due to aging galvanized pipes, which are rusting and corroding. Work has been done over the years by multiple contractors, and as a result, it is not a uniformed system and not as effective. | 2001 SW 4th Avenue | Future | 1614400 | 0 | 0 | 0 | 1614400 | 0 | 0 | 0 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
Office Building Roof Replacement - Lauderdale Memorial Park Cemetery | NEW-FY 20240003 | OTHPHEV | The City conducted an assessment of the office building roof. The results showed the roof to be in poor condition, and the recommendation was for a full roof replacement. However, recent repair efforts by City staff have been successful, extending the life expectancy by another 2-3 years. By FY 2026, a full replacement of the roof is recommended. | 2001 SW 4th Avenue | Future | 0 | 180000 | 0 | 0 | 180000 | 0 | 0 | 0 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
Regional Renewal & Replacement | P00401 | WATERSEWER | Provides for current and future needs, as noted in the Wastewater Master Plan and annual Central Region Renewal and Replacement report. | Citywide | Future | 4922380 | 5620334 | 13847325 | 7462410 | 31852449 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Enterprise Resource Planning (ERP) | P11937 | FINADMIN | The City's current financial applications are over ten years old, and is supporting multiple business packages from different vendors on multiple operating system software programs running on hardware that will no longer be supported. These systems are only partially integrated, and require extensive human intervention. The City is seeking to reduce costs and become more efficient by standardizing to one database and one vendor that would encompass a suite of financial modules and sub modules that would share data between departments, this will eliminate time-consuming and inefficient duplicate key-punching. | 100 North Andrews Avenue | Future | 300000 | 273000 | 240400 | 275000 | 1088400 | -1 | -1 | -1 | -1 | ITS | Yes | Information Technology Services | Information Technology Services
Bridge Restoration | P12010 | BRIDGES | Most of the bridges have exposed and rusted reinforcement. In time, if these reinforcements are not protected, these bridges will not be able to carry vehicular loads. Restoration consists of protecting these rebars with epoxy coating in order to slow down the deterioration and limit the damages already inflicted on these bridges. Paint coating will be applied if it is required on the bridge surface to protect it from hairline cracks not repaired by the epoxy coating. | City-wide | Future | 0 | 0 | 1500000 | 1500000 | 3000000 | -1 | -1 | -1 | -1 | MGR | Yes | City Manager | City Manager
Facility Assessment - Roofing Priorities | P12161 | OTHGEN | Roofing projects are identified and prioritized during regular inspections or if damage or leaks are reported. | Various Locations | Future | 500000 | 500000 | 500000 | 700000 | 2200000 | -1 | -1 | -1 | -1 | MGR | Yes | City Manager | City Manager
Facility Assessment - HVAC Priorities | P12162 | OTHGEN | Heating, ventilating, and air conditioning (HVAC) system and electrical projects are identified and prioritized during regular inspections or as damages and deficiencies are reported. | Various Locations | Future | 1000000 | 1000000 | 1000000 | 700000 | 3700000 | -1 | -1 | -1 | -1 | MGR | Yes | City Manager | City Manager
Facility Assessment - Exterior Repair / Construction | P12163 | OTHGEN | Exterior repair and construction projects are identified and prioritized during regular inspections or as damages and deficiencies are reported. | Various Locations | Future | 250000 | 250000 | 250000 | 700000 | 1450000 | -1 | -1 | -1 | -1 | MGR | Yes | City Manager | City Manager
Facility Assessment - Interior Repair/Construction | P12164 | OTHGEN | Interior repair and construction projects are identified and prioritized during regular inspections or as damages and deficiencies are reported. | Various Locations | Future | 250000 | 250000 | 250000 | 700000 | 1450000 | -1 | -1 | -1 | -1 | MGR | Yes | City Manager | City Manager
George T. Lohmeyer Wastewater Treatment Plant Motor Control | P12176 | WATERSEWER | There are many Motor Control Centers within the facility that are past their useful life and are no longer supported with parts and materials by the original manufacturers. | 1765 SE 18 Street | Future | 0 | 7355588 | 7355588 | 0 | 14711176 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Parking Administration and City Parking Garage Rep | P12183 | PARKING | This request is to ensure that in 2026 and 2028, after the first phase of repairs are completed, TAM is able to dedicate funding to proceed to the second and third phase of the Riverwalk's respective repairs. Requested amount: FY26 $1,500,000 and FY28 $1,500,000. | 150 SE 2nd Street | Future | 0 | 1500000 | 0 | 1500000 | 3000000 | 0 | -1 | 0 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
Melrose Park Street Lighting | P12309 | HUD | Melrose Park residents in Commissioners District 3 are requesting the City to provide new street lights in their neighborhood. There is no existing lighting. Reasons for the new street lights are for safety of the homeowners who live, walk and drive in the neighborhood. | Melrose Park Community | Future | 0 | 0 | 0 | 1274100 | 1274100 | 0 | 0 | -1 | 0 | MGR | Yes | City Manager | City Manager
NE 4th Street Improvements | P12318 | ROADST | This project supports the City Commission Priority of creating transportation network where people can move through the city as development in downtown increases by completing a missing sidewalk connection in downtown adjacent to many new developments on NE 4th Street between US1 and NE 3rd Avenue. Additionally, the District Commissioner has requested status of completion of this project. This project was previously funded through the Downtown Walkability Program that implemented the Plan completed in 2013. The implementation was defunded to fund the Las Olas Boulevard Vison Plan. Design plans were completed with input from adjacent property owners and are awaiting implementation. | NE 4th Street | Future | 0 | 0 | 0 | 1250000 | 1250000 | 0 | -1 | 0 | 0 | MGR | Yes | City Manager | City Manager
City-Owned Seawall Restoration and Replacement | P12330 | FLDSTRM | The City owns approximately five miles of seawalls. Many of these seawalls are adjacent to City-owned roadways and show signs of deterioration and potential failure. Seawall failure could negatively impact navigation, threaten the stability of the soil embankment, and ultimately cause roadway failure. As a coastal community, the City must prepare for the impacts of climate change. Expected sea level rise according to the 2019 Unified Sea Level Rise Projection for SE Florida is 10 to 17 inches above 2000 mean sea levels by 2040 and 21 to 40-inches above 2000 mean sea levels by 2070. Many of the City-owned seawalls are currently being overtopped during extreme high tides on a regular basis. The Citys Seawall Master Plan provides guidance on which seawalls need to be replaced and elevated in five year planning increments. To meet community needs for an improved level of service due to a sea level rise and increased storm events, the City must address the current height of seawalls. | City-wide | Future | 484100 | 1000000 | 1500000 | 2000000 | 4984100 | -1 | -1 | 0 | -1 | MGR | Yes | City Manager | City Manager
Parker Playhouse Renovation | P12343 | SPECREC | Parker Playhouse was one of Fort Lauderdale's first theatre venues in operation since 1967 featuring some of the finest entertainment, concerts, comedy, theater, and family programming. This 1,167 seat theater plays an important role in the community by fueling economic development while also bringing the community together with performances, activities, and educational programming. These renovations are extremely needed to update this aging facility. | 707 NE 8th Street | Future | 700000 | 700000 | 700000 | 185000 | 2285000 | 0 | -1 | 0 | 0 | MGR | Yes | City Manager | City Manager
Program Management of Consent Order Projects | P12375 | WATERSEWER | These services will be required in order to complete and deliver in a timely manner the projects and services outlined in the Consent Order Agreement between the City and Florida Department of Environmental Protection. | City-Wide | Future | 1392890 | 1163724 | 0 | 0 | 2556614 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
NW 13th Street 24" Force Main Replacement | P12388 | WATERSEWER | This existing 24-inch section of force main is one of the oldest in the City's system, and has far exceeded its life cycle, making it susceptible to breakage and possible sanitary sewer overflows (SSO). For these reasons, this section of force main has been identified for evaluation and rehabilitation as needed, per Exhibit C of the Consent Order Agreement. | NW 13th Street from SR 845 to SR 811 | Future | 0 | 871608 | 0 | 0 | 871608 | 0 | -1 | 0 | 0 | PWD | Yes | Public Works | Public Works
Peele-Dixie WTP Chemical Storage Improvements | P12403 | WATERSEWER | This is a 2016 Comprehensive Utility Strategic (CUS) Master Plan recommendation. Due to additional chemical addition, the bulk tanks cannot accept a full delivery and wastes money spent on a full load of chemicals that is not utilized by the City. | 1500 South State Road 7 | Future | 0 | 0 | 1364012 | 0 | 1364012 | 0 | 0 | -1 | 0 | PWD | Yes | Public Works | Public Works
Watermain Improvements Area 1 | P12416 | WATERSEWER | This is a 2016 Comprehensive Utility Strategic Master Plan recommendation. The 54-inch pipe was closed for maintenance, but it has not been put back into service because of inability to disinfect. There are a variety of head loss and capacity issues around the water treatment plant when it is offline. The other locations had a variety of head loss and capacity issues around the water treatment plant (Velocity > 5 ft/s). This project is included in the Infrastructure Renewal Strategic Initiative. | NW 38th Street near Fiveash WTP | Future | 1297110 | 0 | 0 | 0 | 1297110 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Public Works Joint Facility | P12446 | ROADST | The City-owned property where the meter shop team operated out of has been sold, and the stormwater operations team has outgrown their available space at the Central Maintenance Services (CMS) site. These Public Works divisions, alone with the new roadway maintenance team, need a base of operations. Current City facilities do not have the capacity nor were they designed to store the equipment and offices for these crews. | 6001 Hawkins Road | Future | 0 | 4000000 | 0 | 0 | 4000000 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
George T. Lohmeyer Wastewater Treatment Plant Chlorine Scrub | P12468 | WATERSEWER | The scrubber has a useful life of ten (10) years according to the Central Region Wastewater System Renewal and Replacement Requirement Analysis. This scrubber was installed in 2006. The scrubber is an integral part of the facility's Risk Management Plan and must be maintained according to this plan. | 1765 SE 18th Street | Future | 0 | 525400 | 0 | 0 | 525400 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Lifeguard Tower Replacements | P12503 | OTHPHEV | The Ocean Rescue bureau currently operates from twenty (20) lifeguard towers. These towers are specifically designed for Ocean Rescue services and meet all the criteria of a modern lifeguard tower. The average life expectancy of these towers are approximately twenty (20) years in the coastal environment of Fort Lauderdale. Initially, staff replaced four (4) aged lifeguard towers that were purchased in the 1980’s. The current request is to fund the remaining sixteen (16) lifeguard towers, with three (3) towers set to be replaced in fiscal year (FY) 2023, based on their anticipated end of life cycle. | Fort Lauderdale Beach Boulevard - A1A | Future | 196007 | 209727 | 224408 | 235628 | 865770 | -1 | -1 | 0 | -1 | MGR | Yes | City Manager | City Manager
Annual Concrete & Paver Stones Contract | P12517 | ROADST | The City prioritizes providing safe and accessible sidewalks that comply with ADA (Americans with Disabilities Act) standards. This project allows the City to repair and maintain concrete sidewalks and amenities, including pavers and edge beams, within the right of way. The sidewalk deficiencies to be addressed, with this project, range from cracked concrete sidewalks to differential settlement, which present significant public safety issues. In June 2020, the City Commission approved the sidewalk repair ordinance whereby the City assumed responsibility for the repair and replacement of sidewalks, except when determined that the abutting property owner had damaged the sidewalk. The revised ordinance has led to a significant increase in the number of requests for sidewalk repairs. | Citywide | Future | 1500000 | 1500000 | 2000000 | 2000000 | 7000000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Annual Asphalt Resurfacing | P12518 | ROADST | Street resurfacing is needed to improve streets affected by utility work and that have a Pavement Condition Index (PCI) below 55. | Citywide | Future | 500000 | 500000 | 1000000 | 1000000 | 3000000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Annual Asphalt Resurfacing | P12518 | ROADST | Street resurfacing is needed to improve streets affected by utility work and that have a Pavement Condition Index (PCI) below 55. | Citywide | Future | 1000000 | 1000000 | 1000000 | 1100000 | 4100000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Utilities Emergency Operations Center & Administration Build | P12526 | WATERSEWER | This project will be for the design and construction of a Utilities Emergency Operations Center within the existing Administration Building located at 949 NW 38th Street, which will serve as the nerve center for all Utilities Operations during hurricanes and emergencies. This will allow for full monitoring of all three (3) plants and Supervisory Control and Data Acquisition (SCADA) signals for all pump stations. Also, included as part of this project, is to renovate the Administration Building on site, which will encompass mold remediation, reconfiguring office spaces within the building/floors/breezeway to accommodate new chiefs/staff for the afternoon/night shifts, and exterior impact improvements. | 949 NW 38th Street | Future | 0 | 0 | 3168933 | 0 | 3168933 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Runway 27 By-Pass Taxiways | P12540 | AIRPORTS | The construction of the two by-pass taxiways will provide additional runway crossings, as well as, an additional runway entrance that will assist in reducing queue congestion at the runway end. The reconfigured run-up area will allow for more aircraft to stage prior to clearance for take-off and provide adequate separation from one another. The project is listed in the airports current Airport Layout Plan (ALP). | 6000 NW 21st Avenue | Future | 0 | 20000 | 30000 | 0 | 50000 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 27 By-Pass Taxiways | P12540 | AIRPORTS | The construction of the two by-pass taxiways will provide additional runway crossings, as well as, an additional runway entrance that will assist in reducing queue congestion at the runway end. The reconfigured run-up area will allow for more aircraft to stage prior to clearance for take-off and provide adequate separation from one another. The project is listed in the airports current Airport Layout Plan (ALP). | 6000 NW 21st Avenue | Future | 0 | 108650 | 15000 | 0 | 123650 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Runway 27 By-Pass Taxiways | P12540 | AIRPORTS | The construction of the two by-pass taxiways will provide additional runway crossings, as well as, an additional runway entrance that will assist in reducing queue congestion at the runway end. The reconfigured run-up area will allow for more aircraft to stage prior to clearance for take-off and provide adequate separation from one another. The project is listed in the airports current Airport Layout Plan (ALP). | 6000 NW 21st Avenue | Future | 0 | 1955700 | 270000 | 0 | 2225700 | -1 | 0 | 0 | 0 | MGR | Yes | City Manager | City Manager
Roadway and Sidewalk Replacements | P12542 | HUD | This project is for the replacement of roadways and sidewalks identified throughout the City that have been identified as poor, very poor, serious, and failed conditions according to the Asphalt Pavement Condition Index (PCI) 0-55 categorization. | City-Wide | Future | 500000 | 500000 | 500000 | 550000 | 2050000 | -1 | -1 | -1 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
Water Tower Lighting | P12545 | PARKREC | The water tower is a highly visible local feature and the lighting could match other public amenities including the new Las Olas parking garage. The water tower is viewable from many high -traffic pedestrian areas including the Sistrunk corridor and installing the decorative lighting system to the water tower could bring a positive evening enhancement to the environment and area. | 625 NW Second Avenue | Future | 0 | 0 | 500000 | 0 | 500000 | 0 | -1 | 0 | 0 | PRD | Yes | Parks and Recreation | Parks and Recreation
NE 1st Street Bridge Replacement | P12597 | BRIDGES | The Florida Department of Transportation (FDOT) issued a bridge deficiency letter indicating that this bridge has significant structural deficiencies and needs immediate attention. The bridge has been identified as scour critical by FDOT. The bridge is 80 years old, and the concrete elements are probably contaminated with chloride and have significant deterioration. | North Victoria Park Road at NE 1st Street | Future | 1568500 | 0 | 0 | 0 | 1568500 | 0 | -1 | 0 | 0 | MGR | Yes | City Manager | City Manager
George T. Lohmeyer Wastewater Treatment Plant Building Infra | P12602 | WATERSEWER | Most buildings within GTL are approximately 40 years old, but due to corrosion, some components can appear to be closer to 75 years old. Other Capital Improvement Plan projects are addressing the reduction of corrosive gases and moisture. These components must be replaced. | 1765 SE 18th Street | Future | 220000 | 0 | 0 | 0 | 220000 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Mausoleums - Lauderdale Memorial Gardens Cemetery | P12717 | OTHPHEV | Currently the cemetery division is at full capacity due to increased demand for mausoleums. As a result, the City is missing out on revenue opportunities to both finance operations and properly maintain the perpetual care trust fund. Although in-ground burials remain popular a growing number of individuals are finding added prestige to be entombed inside of a structure. And for the loved ones left behind community mausoleums offer convenience for visiting in any weather. | 2001 SW 4th Avenue | Future | 360916 | 0 | 0 | 0 | 360916 | 0 | 0 | 0 | -1 | MGR | Yes | City Manager | City Manager
Lead and Copper Rule Revision (LCRR) Compliance Program | P12787 | WATERSEWER | The Lead and Copper Rule (LCR) is a United States federal regulation (40 CFR 141.80 et seq.) requires all regulated water systems complete a comprehensive materials inventory by the anticipated compliance date of October 16, 2024. The inventory must include all service lines connected to the public water distribution system regardless of ownership status (e.g., where service line ownership is shared, the inventory would include both the portion of the service line owned by the water system and the customer-owned portion of the service line) | City-Wide | Future | 3000000 | 3400000 | 0 | 0 | 6400000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Bayview Drive Bridge Over Longboat Inlet Replacement | P12790 | BRIDGES | This bridge is in poor condition based on the National Bridge Inspection Standards and Florida Department of Transportation (FDOT) guidelines. The bridge is classified as both functionally obsolete and structurally deficient by Florida Department of Transportation (FDOT). The bridge currently has a sufficiency rating of 37. The bridge has been identified as scour critical by FDOT because the foundations are unknown. The bridge is currently 58 years old. There are no feasible and prudent ways to protect low lying pre-stressed concrete slab bridges which are chloride contaminated. | Bayview Dr. North of NE 55th PL | Future | 1908700 | 0 | 0 | 0 | 1908700 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
SE 13th Street Bridge Replacement | P12791 | BRIDGES | This bridge is 62 years old and has been identified as scour critical by Florida Department of Transportation (FDOT) and classified as functionally obsolete but not structurally deficient. The T-beams need numerous repairs because of the cracks, spalls, and delaminations. The most cost effective way to fix these repairs is to replace the entire bridge. Florida Department of Transportation (FDOT) Bridge Inspection Pontis report (Bridge Report Management) gives a sufficiency rating of 43, indicating a high priority for repair. | SE 13th Street | Future | 2542326 | 3733200 | 0 | 0 | 6275526 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Streetlight Improvements | P12793 | PARKREC | The Fort Lauderdale Street Lighting Master Plan established lighting level standards and guidelines for light assemblies (i.e. poles and fixtures). The Master Plan also established estimated costs to bring existing streetlights and corridors at specific pilot locations up to these new standards. The City’s streetlight network includes approximately 15,000 to 20,000 lights along 809 miles of streets. Most of these lights are owned by Florida Power and Light (FPL); the remaining lights are owned by the City, County, Florida Department of Transportation (FDOT), and private developers. The outcomes, over time, will be a consistent look, feel, and function of streetlights as well as safer streets that cost less to light and maintain. | Citywide | Future | 500000 | 500000 | 500000 | 1000000 | 2500000 | -1 | -1 | -1 | -1 | PRD | Yes | Parks and Recreation | Parks and Recreation
Las Olas Mobility | P12796 | ROADST | To enhance safety and mobility for all who access Las Olas Boulevard between S. Andrews Avenue and A1A to live, work, or play. In June 2021, the Fort Lauderdale City Commission voted to endorse the Las Olas Conceptual Design Visions for the Eastern and Western Corridors. This was also a 2020 and 2021 City Commission priority. | Las Olas Blvd | Future | 1500000 | 0 | 0 | 0 | 1500000 | 0 | -1 | 0 | -1 | TAM | Yes | Transportation & Mobility | Transportation & Mobility
George T. Lohmeyer Wastewater Treatment Plant Reactor Rehabi | P12800 | WATERSEWER | The 2017 Comprehensive Utility Strategic Master Plan (CUSMP) recommends more efficient oxygen transfer at the plant." Currently, the two reactors are located on a concrete pad that is more than forty years old and in need of repair." | 1765 SE 18th Street | Future | 1273600 | 3080000 | 0 | 0 | 4353600 | 0 | 0 | 0 | -1 | PWD | Yes | Public Works | Public Works
Fiveash Water Treatment Plant Filters Rehabilitation | P12804 | WATERSEWER | This will improve the water quality process at Fiveash Regional Water Treatment Plant. | 3501 W Prospect Road | Future | 0 | 0 | 0 | 750000 | 750000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works
Laudergate Isles Small Watermain Improvements | P12823 | WATERSEWER | The Water Master Plan identifies the replacement as necessary. This will also improve quality of service by improving pressure and reducing water quality complaints. | 2112 NE 14th Court | Future | 0 | 0 | 444773 | 0 | 444773 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
Basin A-22 Sanitary Sewer Collection System Rehabilitation | P12829 | WATERSEWER | Inflow and Infiltration (I&I) from storm events and tidal events creates a burden on sewer assets including pipes, laterals, manholes, pump stations, and plants. Lining of pipes, laterals, and manholes reduces the inflow and infiltration while rehabilitating the assets and creating a new asset with a 50-year service life at a fraction of the cost of open cut replacement. This sewer basin area was identified as part of the 2019 Florida Department of Environmental Protections (FDEP) Capacity Evaluation Report to be rehabilitated. The report identifies this basin as a high priority as it is prone to sanitary sewer overflows, leading to high pump station run times and ultimately, excessive inflow and infiltration contribution to the George T. Lohmeyer Wastewater Treatment Plant. | NE 15th Avenue and NE 15th Street | Future | 0 | 0 | 4167118 | 0 | 4167118 | -1 | 0 | 0 | 0 | PWD | Yes | Public Works | Public Works
EV Charger Installation at City Facilities | P12833 | ROADST | City staff need to prepare for the transition of its fleet to electronic vehicles. The majority of vehicle manufacturers are moving production towards EVs. By 2030, the expectation is that staff will not have the option to purchase a standard gas-powered vehicle. Additionally, in December 2021, the City Commission passed a resolution calling for net zero greenhouse gas emissions in City operations by 2040. With approximately 27% of all greenhouse gas emissions coming from the transportation sector, a big driver for achieving net zero emissions in City operations will come through the transition to EVs. | Citywide | Future | 100000 | 100000 | 100000 | 0 | 300000 | -1 | -1 | -1 | -1 | PWD | Yes | Public Works | Public Works